## Hárok1
Pripomienky k pripravovanému národnému projektu s názvom "Cloudové služby GOVNET"
p.č. | Zadávateľ pripomienky/subjekt | Typ dokumentu (Projektový zámer, Prístup k projektu, CBA) | Kapitola | Strana | Príslušný text | Pripomienka | Vysvetlenie/návrh riešenia/návrh zámeny/ doplnenia textu dokumentu | Typ závažnosti pripomienky [Vysoká, Stredná, Nízka] | Stav zapracovania pripomienky [Zapracovaná, Zamietnutá, Vysvetlená, Nevyriešená] | Vyjadrenie spracovateľa
1 | Slovensko.Digital | Projektovy zamer | koncepcne cely dokument |  |  | Uplne jasne sa ukazuje absencia strategie vladneho cloudu v kontexte komunitnych cloudov, ktora by definovala principy a standardy komunitnych cloudov, definovala zakladnu high-level architekturu (funkcnu, organizacnu, technologicku, bezpecnostnu a pod.), governance principy a plan budovania. Projektovy zamer Nases je izolovanym projektom, technicky respektujucim len vybrane prostredie, bez jasnych principov a pravidiel, bez kvalitativnych parametrov, nezapada do sirsej strategie. |  | Vysoka
2 | Slovensko.Digital | Projektovy zamer | koncepcne cely dokument |  |  | Projektove zamery na jednotlive komunitne cloudy nemozu byt posudzovane samostatne, izolovane ale musia byt posudzovane spolocne ako jeden program a tak aj riadene. Preto je potrebne najprv pripravit strategiu a jednotlive zamery by mali z nej vychadzat a az nasledne by sa mali pustat do implementacie. Zaroven je potrebne v ramci tohto programu hodnotit aj uz doteraz realizovane investicie do privatnej casti vladneho cloudu, ktoru prevadzkuje MV SR. |  | Vysoka
3 | Slovensko.Digital | Projektovy zamer | koncepcne cely dokument |  |  | Projektovy zamer Nases je koncepcne postaveny na zlych predpokladoch: hybridny rezim nie je v projektovom zamere povinnost ale len moznost. Sme nazoru, ze vsetky aktivity v budovani cloudovych sluzieb v ramci statu by mali byt postavene na hybridnom modeli, v ktorom plati princip public cloud first. Tento princip zabezpeci skalovatelnost, flexibilitu a nakladovu efektivnost privatna cast vladneho cloudu je benchmarkom pre nove navrhovane riesenie. Sme nazoru, ze v pripade budovania novych privatnych casti by benchmarkom mali byt public cloudy a nie zastarale, riesenie, ktoreho nedostatky popisuje aj projektovy zamer. Toto by mal byt principialny pohlad pre cely projektovy zamer zamer je koncipovany vylucne ako CAPEX. OPEX zmyslanie uplne absentuje a toto shapuje dizajn projektoveho zameru, posudzovane alternativy a pod. |  | Vysoka
4 | Slovensko.Digital | Projektovy zamer | koncepcne cely dokument |  |  | Projektovy zamer Nases ako argumentacnu bazu vyuziva Gartner. Dovolujeme si doplnit dalsie tvrdenia z Gartnera pre sirsi obraz o budovani government cloudov, ktorym v podstate je aj komunitny cloud Nasesu:This leads Gartner to expect that governments will implement private cloud at twice the rate of public cloud through 2021, despite private cloud not delivering the same benefits in scale, functionality, cost savings or agility as public cloud." Government private cloud is the new legacy." Much of what governments report as "private cloud" is better categorized as advanced virtualization or outsourced IT infrastructure. These may still be excellent environments for running certain workloads, but are unlikely to have all the benefits of a true private cloud. The gap between what government private clouds can realistically achieve and functionality delivered by the public cloud is growing. "Government private cloud is the new legacy," says Cannon. A Gartner survey revealed that less than 5% of private cloud environments in government actually have the full characteristics of cloud. "What this highlights is that there are political benefits to talking about moving to cloud, even where that transition is not taking place in a meaningful way," explains Cannon. "Poor or incomplete cloud implementations have the potential to produce the worst of both worlds, leaving government employees and citizens poorly served in the end." |  | Vysoka
5 | Slovensko.Digital | Projektovy zamer | KPI |  |  | KPI - ziadny z KPI nie je orientovany na benefity, ktore cloud ma prinasat. KPI na meranie cloudu ma byt efektivnost a to nakladova, casova, zdrojov a pod. KPI aktualne uvedene v ramci projektoveho zameru nepovazujeme za relevantne. Jednotlive formy efektivnosti by mali byt principom pre spracovanie takehoto projektoveho zameru. |  | Vysoka
6 | Slovensko.Digital | Projektovy zamer/Pristup k projektu | Alternativy |  |  | Najprv mali byt pomenovane biznis alternativy a potom technologicke alternativy pre biznis alternativy. Alternativy su postavene na CAPEX zmyslani a diferenciu robi len skala SaaS sluzieb. Uplne absentuju alternativy postavene na OPEX nakladoch ako je prenajom riesenia, pripadne jeho casti, pripadne hybridny model. Projektovy zamer na viacerych miestach argumentuje latenciou, zlou konektivitou a bezpecnostou globalnych hracov. Dovolujeme si upozornit, ze existuju lokalni poskytovatelia cloudovych sluzieb, ktori maju niekolkonasobnu kolokacnu kapacitu v MW, slovensky a zahranicny peering, priame prepojania do Amsterdamu a Frankfurtu, moznost pripojenia OVM cez DF s kapacitou az stoviek Gbs, bezpecnostne certifikacie, audity KB podla 69/2018. Tento fakt nie je nijak zohladneny v ramci alternativ a ani CBA. |  | Vysoka
7 | Slovensko.Digital | Projektovy zamer | ToBe stav |  |  | To Be stav je postaveny na Oracle infrastrukture. Toto definuje, ze do takehoto prostredia nebude mozne umiestnit napr. ziadne SAP riesenia. Zaroven SAP sa na taketo prostredie bude pozerat ako na on-premise a tak aj bude licencovat svoje produkty, co je najnevyhodnejsi model licencovania. V projektovom zamere uplne absentuje analyza IT rieseni, ktore by mali byt umiestnene do navrhovaneho prostredia a to v rozsahu, ci ich tam vobec bude mozne umiestnit a ake s tym budu spojene naklady (migracia, licencovanie, atd). V projektovom zamere je uvedenych 6 IT rieseni, ktore by mali v prostredi prevadzkovane. Musia vsetky bezat v privatnej casti, ani jedno z rieseni alebo jeho cast nemoze bezat v public cloude? Uplne absentuje posudenie umiestnenia tychto jednotlivych IT rieseni do navehovaneho prostredia. Public cloudy aktualne ako dolezity parameter riesia energeticku efektivnost a minimalnu zataz prostredia. Tento rozmer uplne v projektovom zamere absentuje. |  | Vysoka
8 | Slovensko.Digital | CBA |  |  |  | CBA nepovazujeme za relevantnu. OPEX naklady za neralne. Absentuju naklady za kolokaciu, elektricku energiu. Personalne naklady su podhodnotene - 2 architekti, 2 analytici a 1 bezpecak je nedostatocny pocet. Ma byt zabezpecena prevadzka 24/7? Ma byt podpora L1 az L3? Absentuju naklady, ktore budu spojene s migraciou jednotlivych IT rieseni do tohto prostredia. CBA by mala byt postavena na porovnani sa nakoniec s public cloudom. |  | Vysoka
9 | Slovensko.Digital
10 | Slovensko.Digital
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30